# Work Plan (GANTT) - ARISE Project

Total Duration:24 Months (January 2026 – December 2027)

### WP1: Project Management, Requirements and Dissemination

- Duration:M1 – M24 (Transversal)

- Objective:Project management, definition of clinical and technical requirements, compliance management and dissemination of results.

- Deliverable Key:

  - D1.1 (M3):Clinical Requirements and Biomechanical KPIs Document (with DYNOGMS).

  - D1.2 (M6):TRL6 Validation Protocol and submission to the Ethics Committee (with Studio Buccarella).

  - D1.3 (M24):Final report and dissemination plan.

| Task | Activity | M1-M6 | M7-M12 | M13-M18 | M19-M24 |
| --- | --- | --- | --- | --- | --- |
| T1.1 | Project Management e Coordinamento | X | X | X | X |
| T1.2 | Compliance Management (GDPR/MDR) and Data | X | X | X | X |
| T1.3 | Definition of Clinical Requirements and Protocol (with Partners) | X |  |  |  |
| T1.4 | Dissemination and Exploitation of Results |  |  |  | X |

### WP2: Market Analysis and System Architecture

- Duration:M3–M9

- Objective:Define the market strategy (vs. state of the art) and design the software/cloud architecture and user interfaces.

- Deliverable Key:

  - D2.1 (M9):Market Analysis Document (vs. Pressure Plates) and Cloud/Edge Architecture.

  - D2.2 (M9):UI/UX Specifications and Mockups (Patient and Therapist).

| Task | Activity | M1-M6 | M7-M12 | M13-M18 | M19-M24 |
| --- | --- | --- | --- | --- | --- |
| T2.1 | Cloud Architecture and Data Protocol Definition (with Invenio) | X | X |  |  |
| T2.2 | Market Approaches and Strategy Analysis (with Invenio) | X |  |  |  |
| T2.3 | UI/UX Design (Coach and Dashboard) (with Invenio) | X | X |  |  |

### WP3: Core AI Research and Hardware Design

- Duration:M6 – M15 (Industrial Research)

- Objective:Create the AI ​​assets (measurement and forecasting) and engineer the “Coach” device.

- Deliverable Key:

  - D3.1 (M9): ReportSensor Comparison Study (RGB/RGBD/NOSE).

  - D3.2 (M15):AI models (3D Pose + Forecasting) trained andvalidated.

  - D3.3 (M12):Hardware Design and Planning Document (T3.5).

| Task | Activity | M1-M6 | M7-M12 | M13-M18 | M19-M24 |
| --- | --- | --- | --- | --- | --- |
| T3.1 | Comparative Study of Sensors (RI Prototypes) (with Invenio) | X | X |  |  |
| T3.2 | STS Dataset Acquisition and Annotation (with Clinical Partners) |  | X | X |  |
| T3.3 | 3D Measurement AI Model Development (with Invenio) |  | X | X |  |
| T3.4 | Predictive AI Model Development (Forecasting) (with Invenio) |  | X | X |  |
| T3.5 | "Coach" Hardware Design and Cloud Platform |  | X |  |  |

### WP4: Platform Prototyping (Hardware and Software)

- Duration:M12 – M18 (Experimental Development)

- Objective:Build and integrate the TRL6 system (Coach Device and Clinical Dashboard).

- Deliverable Key:

  - D4.1 (M18):TRL6 prototype (n. 5-10 "Coach" units + Cloud Platform) integrated and tested in the laboratory.

| Task | Activity | M1-M6 | M7-M12 | M13-M18 | M19-M24 |
| --- | --- | --- | --- | --- | --- |
| T4.1 | "Coach" Hardware Prototyping (Experimental Development) |  | X | X |  |
| T4.2 | On-Device Software Development and Biofeedback (with Invenio) |  | X | X |  |
| T4.3 | Backend Developmente Frontend"Clinical Dashboard" (with Invenio) |  |  | X |  |
| T4.4 | System Integration and Testing (Hardware/Software/AI) |  |  | X |  |

### WP5: TRL6 Clinical Validation and User Testing

- Duration: M19 – M24

- Objective:Demonstrate and validate the effectiveness, accuracy and usability of the system in a real clinical environment.

- Deliverable Key:

  - D5.1 (M24): Report finaleTRL6 Validation (Accuracy vs Gold Standard DINOGMI; Usability vs Buccarella Study).

| Task | Activity | M1-M6 | M7-M12 | M13-M18 | M19-M24 |
| --- | --- | --- | --- | --- | --- |
| T5.1 | Clinical Setup (Installation at Studio Buccarella) |  |  |  | X |
| T5.2 | Clinical Trial Execution (with Real Patients) |  |  |  | X |
| T5.3 | Usability Feedback Collection (Patients and Therapists) |  |  |  | X |
| T5.4 | Data Analysis and Accuracy Validation (with DINOGMI) |  |  |  | X |